## BackLog
As | Resume of the Tasks | Estimated Duration (Half Day) | Current State | Notes | End of Task Day / Hours
Player | I can connect myself to the server | 2 | Completed | Port 26 999. Need to test with LudusVR's PC. | 05/01 - 16H
Dev | I need to have in my possession all necessary assets | 1 | Completed |  | 10/01 - 16H
Player | I can move my character and see the other character moving | 1 | Completed |  | 05/01 - 18H
Player | I can control my camera | 1 | Completed |  | 10/01 - 12H
Player | I have skin and animation in my character | 2 | Completed |  | 11/01 - 12H
Player | I can jump and see the other character jump | 1 | Completed |  | 10/01 - 18H
Dev | I need to write a Level Design Document | 1 | Completed |  | 11/01 - 18H
Dev | I need to structure the architecture of the map | 1 | Completed |  | 11/01 - 16H
Player | I can see a life bar and spell icones | 1 | Completed |  | 12/01 - 14H
Dev | I need to create a first monster (who detects players, can run toward players and can damage them) | 2 | Completed |  | 18/01 - 13H
Player | I can hit enemies | 0.5 | Not Started |  | 19/01 - 16H
Player | I can see the other player hit enemies | 0.5 | Not Started
Player | I can shield myself | 0.5 | Completed |  | 19/01 - 18H
Player | I can see the other player shield itself | 0.5 | Not Started
Player | I can put a glyph | 0.5 | Completed |  | 24/01 - 11H
Player | I can see the other player's glyph | 0.5 | Canceled | Need clarity on the map. | -
Player | I can teleport myself in my glyph | 0.5 | Completed |  | 24/01 - 13H
Player | I can see the other player teleport himself | 0.5 | Completed |  | 24/01 - 13H
Player | I can dash | 0.5 | Canceled | There is already a teleportation in game | -
Player | I can see the other player dash | 0.5 | Canceled | There is already a teleportation in game | -
Player | I can regenerate point of life when I hit in the back on the enemy | 1 | Completed |  | 25/01 - 13H
Player | I can activate door and bridge | 1 | Completed |  | 24/01 - 18H
Dev | I need to control when a player die | 1 | Completed |  | 19/01 - 13H
Dev | I need to embellish the map | 1 | Completed |  | 17/01 - 13H
BONUS (not necessary for the prototype)
Dev | I need to create a boss | 2 | Not Started
Dev | I need to create an other monster (who detects players, can run toward players and can damage them) | 1 | Not Started
Player | I can hurt a mortal trap or a healing totem | 1 | Not Started
Dev | I can pollish the hub | 1 | Completed |  | 18/01 - 18H
Not Started
Not Started
Not Started
Not Started
Not Started

## Data
Not Started
In Progress
Completed
Paused
Canceled